CAPE COAST SCHOOL FOR THE DEAF (CAPE DEAF)

PROJECT BRIEF AND LOGFRAME

SUBMITTED BY SION AID FOUNDATION

MARCH,2018

TABLE OF CONTENT				……………………………	2

1.0	EXECUTIVE SUMMARY				……………………………	3

2.0	SUMMARY OF MAJOR ACHIEVEMENTS FOR FY 04		…………...	4

3.0	LOGFRAME					……………………………	            5

4.0	2016 IMPLEMENTATION PLAN			……………………………	10

6.0	2016 BUDGET SUMMARY			……………………………	           11

- EXECUTIVE SUMMARY

Cape Coast School for the Deaf (Capedeaf) was established in 60s to educate hearing and speech impaired children in the central region of Ghana. Over the years funding from the central government has not been regular and the school has to depend on donations from individuals and organizations for its management.

The major development goal is to create a conducive environment for the physical, social, academic and spiritual development of 270 hearing and speech impaired children annually.

The following sectors will be the focus of the Project; health, education and Water and Sanitation and project management.

SAFwill work closely with the School Management Committee, Parent – Teacher Association and the Project Management Committee to ensure the achievement of project objectives.

2.0	SUMMARY OF PROPOSED MAJOR INTERVENTIONS FOR 2018

The proposed major interventions are as follows:

  - Vocational Training

Vocational training will be provided for 100 pupils during first year of project implementation and 325 over three year period. This will covere carpentry, dress – making, and agriculture. The training will be done alongside the teaching of the main academic subjects such as English, Mathematics, Social Studies and Integrated Science. The expectation is that these trainings will create employment opportunities for the pupils when they leave school.

A 3-room block which will be completed to serve as the main Training Centre for the pupils. The Centre will be fully equipped.

  - School feeding Programme

School feeding programme will be initiated during the period for 270 school children. Income from the school income generating activities will be used to subsidise the feeding programme. The programme is aimed at improving the health and nutrition profile of the pupils.

  - School Health and Hygiene

The School children will be educated on personal health and hygiene practices. As a result of this, the children acknowledge the need for personal and environmental cleanliness at all times.

Medical check – up will be complementary aspect of the school health programme. Under this, two hundred and seventy children will be screened and treated of various ailments such as malaria, skin rashes and dry cough.

CAPE COAST SCHOOL FOR THE DEAF

PROJECT LOGFRAME

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| Goal To provide a conducive environment for the physical, social, academic and spiritual development of 270 hearing and speech impaired children of cape Coast School for the Deaf. | Number of children (boys and girls) enrolled in school. | Project Reports. | Ghana Education Service will be committed to project goal. |
| HEALTH Purpose 1.0 To improve the nutritional status of 270 hearing and speech impaired children by April 2020. | Percentage of stunted children (boys and girls). | School Health Records. Anthropometric measurement of children (boys and girls) | - School authorities will maintain a commitment to project objectives. |
| Output 1.1 Supplementary feeding programme in place for 270 children. | Number of children (boys and girls) in nutrition programme. | Anthropometric measurement of children (boys and girls). | - Funding will be regular. - Kitchen Department will give children nutritious foods. |
| Activities 1.1.1 Conduct nutrition survey. 1.1.2 Implement supplementary feeding. 1.1.3 Conduct growth monitoring. Total | - Inputs/Resources - Consultancy - Food materials - Weighing scales | Budget $ SAF Ghana Education Service 5,000 0 20,000 0 600 0 25,600 0 |  |

CAPE COAST SCHOOL FOR THE DEAF

PROJECT LOGFRAME

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| EDUCATION Purpose 2.0 270 speech and hearing impaired pupils will have acquired vocational skills by the end of July 2016. | Percentage of pupils (boys and girls) enrolled in vocational skills training. | Project Reports. | Funds will be available to implement project objectives. |
| Output 2.1 Vocational skills training classes held for 270 pupils. | Number of vocational skills training classes held. Number of children (boys and girls) participating. | School Reports Project Reports. | The required equipment will be available. Pupils will demonstrate active interest in vocational skill training. |
| Activities 2.1.1.Rehabiliate Training Centre 2.1.2 Purchase training equipment and materials. 2.1.3 Train 100 pupils in various vocational skills. Total | - Inputs/Resources - Budget - Personnel | Budget $ SAF Ghana Education Service 30,000 0 25,000 500 55 ,000 500 |  |

CAPE COAST SCHOOL FOR THE DEAF (CAPEDEAF)

PROJECT LOGFRAME

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| Purpose 3.0 To strengthen the participation of the School Management Committee (SMC), the Project Committee (PC) and the Parent – Teacher Association (PTA) in the management of Cape Coast School for the Deaf by December 2018. | Increased level of participation of the SMC, PC and PTA in school management. | Project Reports. Interviews | Various committees will see the need to participate in school management. |
| Output 3.0 10 – member SMC, 7 – member PC and PTA Executive trained in community participation in educational management. | Number of committee members (men and women) trained. Number of active committee members (men and women). | Project Reports | Committee members will avail themselves for training sessions. |
| Activities 3.1.1 Develop and print training materials. 3.1.2 Train SMC, PC and PTA members on their roles and responsibilities. 3.1.3 Organise quarterly SMC, PC and PTA meetings to discuss school management issues. Total | - Inputs/Resources - Printing cost. - Training fee - Meeting cost. | Budget $ SAF Community GES 10,000 0 0 3,000 0 0 400 50 0 33,400 50 0 |  |

CAPE COAST SCHOOL FOR THE DEAF (CAPEDEAF)

PROJECT LOGFRAME

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| Purpose 4.0 270 children will have been provided with health check – up, treatment and school uniforms as direct benefit package by September, 2018. | Percentage of children (boys and girls) provided with health screening. | Project Reports. | There will be no budget reduction. |
| Output 4.1 270 children provided with basic school package. | Number of children (boys and girls) provided with direct benefits. | Project Reports. | There will be no budget reduction. |
| Activities 4.1.1 Conduct health screening for sponsored children. 4.1.2 Assess heath status of children. 4.1.3 Regularly monitor the health situation of children. 4.1.4 Educate school children on personal hygiene and HIV/AIDS 4.1.5 Provide school uniforms and stationery. Total | - Inputs/Resources - Drugs. - Nurses - Screening Cards - Medical fees - Nurses - Health Education materials - Budget | Budget $ SAF Community GES 10,000 0 0 8,000 0 0 800 0 0 4,000 0 0 10,000 100 0 5,000 0 0 20,000 0 0 57,800 100 0 |  |

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| ## 05. ANIMAL HUSBANDRY ## Purpose 1.0 To set up a goat farm by September 2006 to generate income. | Percentage of local income generated. | Project Records. | No outbreak of animal diseases. |
| ## Output 5.1 50 goats bred annually. | Number of goats bred. | Project Records. | Healthy breeding stock will be available. |
| # Activities 5.1.1 Construct open shed for goats. 5.1.2 Purchase breeding stock (goats). 5.1.3 Vaccinate goats against diseases. Total | # Inputs Budget Veterinary drugs and services Construction materials. | Budget ($) SAF Community District Assembly 8,000 0 0 2,000 0 0 1,000 0 0 11,000 0 0 |  |

CAPE COAST SCHOOL FOR THE DEAF (CAPEDEAF)

PROJECT LOGFRAME

| Project Summary | Indicators | Means of Verification | Risks & Important Assumptions |
| --- | --- | --- | --- |
| PROJECT MANAGEMENT Purpose 6.0 To ensure the effective management of the Project throughout the three years 2019. | Planning and reporting committements are completed on time. | Annual Plan of Action. Quarterly and Annual Reports. | Project Team will be adequately motivated. |
| Output 8.1 8 – member Project Committee and School Management members trained and able to manage the Project. | Number of Project Committee and School Management Committee members trained. | Project Reports. | Work load of Committee members will allow them to participate in trainings. |
| Activities 6.1.1 Train Project Committee and School Management Committee. 6.1.2 Prepare and submit Monthly, Quarterly and Annual Reports. 6.1.3 Pay for travel and transport expenses. 6.1.4 Pay allowances to Project Committee. 6.1.5 Purchase Office stationery. 6.1.6 Pay for Bank charges Total | - Inputs/Resources - Train materials. - Stationery. | Budget $ SAF Community GES 10,100 0 0 3,000 0 0 8,000 0 0 30,000 0 0 700 0 0 51,700 0 0 |  |

CAPE COAST SCHOOL FOR THE DEAF (CAPEDEAF): IMPLEMENTATION PLAN

| Purpose | Output | Activities | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | HEALTH Output 1.1 Supplementary feeding programme in place for 270 children. | 1.1.1 Conduct nutrition survey. 1.1.2 Implement supplementary feeding. 1.1.3 Conduct growth monitoring. | X X | X | X X X | X X | X | X X | X | X | X | X X | X | X |
| 2.0 | EDUCATION Output 2.1 Vocational skills training classes held for 270 pupils. | 2.1.1 Purchase training equipment and materials. 2.1.2 Train 100 pupils in various vocational skills. | X | X X | X | X | X | X X | X | X | X | X | X | X |
| 3.0 | Output 3.1 10 – member SMC, 7 – member PC and PTA Executive trained in community participation in educational management. | 3.1.1 Develop and print training materials. 3.1.2 Train SMC, PC and PTA members on their roles and responsibilities. 3.1.3 Organise quarterly SMC, PC and PTA meetings to discuss school management issues. | X |  | X | X | X | X | X |  | X |  |  |  |

CAPE COAST  SCHOOL FOR THE DEAF

FY 2018 BUDGET SUMMARY

$

Health 							25,600

Education						55,000

Husbandry                                                                     100,000

Project Management					51,700

Water                                                                           11,000

Total Budget from     SAF     		            196,770

Other Partner Contribution		      	               650

TOTAL BUDGET			        	          158,550